UCT Engineers Without Borders
iSondlo Garden Project
Electronics Team
Prototyping Phase Meeting
30 April 2023

---
Brief
- Divided into 4 phase:
  I. Design and Procurement Phase
  II. Prototyping Phase
  III. Testing Phase
  IV. Implementation Phase

---
Design and Procurement Phase
- Design completed in 2021
- Procurement planning completed in 2022
- Finishing up procurement order for components for testing this week

---
II. Prototyping Phase
Components to start with:
- Arduino with power cables
- Soil Moisture sensors
- Temperature sensors
- 5V Relay Module
- Arduino power cable and wires
- Breadboard